## Internship Tracker
Yenepoya Internship Tracker - 2026
Task ID | Task Description | Project Title | Student Name | Campus ID | Specialization | Semester | Project Timeline | Start Date | End Date | Status | Feedback and Comments
T-001 | Project orientation and internship briefing session with mentor. Understand scope and objectives of the Tejas Raksha security scanner project. | Zero-Day Scanner for Agriculture Web Portals-Tejas Raksha | Giridhar Pai | 25252 | BCA in Cyber Security, Ethical Hacking & Digital Forensics with IBM | 6th Semester | Week 1 - Planning Phase | 2026-03-24 | 2026-03-24 | Completed | Orientation completed successfully. Student understood project goals and deliverables clearly.
T-002 | Literature review on web application security vulnerabilities (OWASP Top 10). Study XSS SQL Injection CSRF and other attack vectors. | Zero-Day Scanner for Agriculture Web Portals-Tejas Raksha | Giridhar Pai | 25252 | BCA in Cyber Security, Ethical Hacking & Digital Forensics with IBM | 6th Semester | Week 1 - Planning Phase | 2026-03-25 | 2026-03-25 | Completed | Good understanding of OWASP Top 10 demonstrated. Notes submitted.
T-003 | Study existing security scanning tools: OWASP ZAP Nikto Burp Suite. Identify gaps and opportunities for the new platform. | Zero-Day Scanner for Agriculture Web Portals-Tejas Raksha | Giridhar Pai | 25252 | BCA in Cyber Security, Ethical Hacking & Digital Forensics with IBM | 6th Semester | Week 1 - Planning Phase | 2026-03-26 | 2026-03-26 | Completed | Comparative analysis document prepared. Mentor approved the approach.
T-004 | Define project requirements: functional requirements user requirements and environmental requirements. Draft initial SRS document. | Zero-Day Scanner for Agriculture Web Portals-Tejas Raksha | Giridhar Pai | 25252 | BCA in Cyber Security, Ethical Hacking & Digital Forensics with IBM | 6th Semester | Week 1 - Planning Phase | 2026-03-27 | 2026-03-27 | Completed | SRS draft submitted. 25 functional requirements and 25 user requirements documented.
T-005 | Technology stack selection and justification. Evaluate Python FastAPI React Docker PostgreSQL Redis Celery for the platform. | Zero-Day Scanner for Agriculture Web Portals-Tejas Raksha | Giridhar Pai | 25252 | BCA in Cyber Security, Ethical Hacking & Digital Forensics with IBM | 6th Semester | Week 1 - Planning Phase | 2026-03-28 | 2026-03-28 | Completed | Technology stack finalized. Justification document approved by mentor.
T-006 | Design system architecture: microservices diagram data flow diagram and component interaction design. | Zero-Day Scanner for Agriculture Web Portals-Tejas Raksha | Giridhar Pai | 25252 | BCA in Cyber Security, Ethical Hacking & Digital Forensics with IBM | 6th Semester | Week 2 - Design Phase | 2026-03-30 | 2026-03-30 | Completed | Architecture diagrams completed. 6-service microservices design approved.
T-007 | Database schema design for PostgreSQL. Design tables for scans false_positives schedules finding_lifecycle and suppression_rules. | Zero-Day Scanner for Agriculture Web Portals-Tejas Raksha | Giridhar Pai | 25252 | BCA in Cyber Security, Ethical Hacking & Digital Forensics with IBM | 6th Semester | Week 2 - Design Phase | 2026-03-31 | 2026-03-31 | Completed | Database schema finalized with 5 tables and proper indexing strategy.
T-008 | API design and endpoint planning. Define 25+ REST API endpoints with request/response schemas and authentication strategy. | Zero-Day Scanner for Agriculture Web Portals-Tejas Raksha | Giridhar Pai | 25252 | BCA in Cyber Security, Ethical Hacking & Digital Forensics with IBM | 6th Semester | Week 2 - Design Phase | 2026-04-01 | 2026-04-01 | Completed | API specification document completed. All endpoints documented with Swagger annotations.
T-009 | UI/UX wireframe design for all 9 pages: Landing Page Scan Progress Results History Schedules False Positives Integrations Trends Documentation. | Zero-Day Scanner for Agriculture Web Portals-Tejas Raksha | Giridhar Pai | 25252 | BCA in Cyber Security, Ethical Hacking & Digital Forensics with IBM | 6th Semester | Week 2 - Design Phase | 2026-04-02 | 2026-04-02 | Completed | Wireframes approved. Dark/light theme design finalized with blue accent color scheme.
T-010 | Set up development environment: Install Docker Desktop WSL2 Python 3.11 Node.js 18 and configure Git repository. | Zero-Day Scanner for Agriculture Web Portals-Tejas Raksha | Giridhar Pai | 25252 | BCA in Cyber Security, Ethical Hacking & Digital Forensics with IBM | 6th Semester | Week 2 - Design Phase | 2026-04-03 | 2026-04-03 | Completed | Development environment fully configured. All tools installed and verified.
T-011 | Create Docker Compose configuration with 6 services: postgres redis api worker beat frontend. Configure networks and volumes. | Zero-Day Scanner for Agriculture Web Portals-Tejas Raksha | Giridhar Pai | 25252 | BCA in Cyber Security, Ethical Hacking & Digital Forensics with IBM | 6th Semester | Week 2 - Design Phase | 2026-04-04 | 2026-04-04 | Completed | Docker Compose setup complete. All 6 containers start successfully with health checks.
T-012 | Initialize FastAPI application with lifespan context manager. Set up database connection pool with SQLAlchemy 2.0 and asyncpg. | Zero-Day Scanner for Agriculture Web Portals-Tejas Raksha | Giridhar Pai | 25252 | BCA in Cyber Security, Ethical Hacking & Digital Forensics with IBM | 6th Semester | Week 3 - Backend Development | 2026-04-06 | 2026-04-06 | Completed | FastAPI app initialized. Async database connection working correctly.
T-013 | Implement SQLAlchemy ORM models: Scan ScanStatus FalsePositive Schedule ScheduleFrequency. Create Alembic migration scripts. | Zero-Day Scanner for Agriculture Web Portals-Tejas Raksha | Giridhar Pai | 25252 | BCA in Cyber Security, Ethical Hacking & Digital Forensics with IBM | 6th Semester | Week 3 - Backend Development | 2026-04-07 | 2026-04-07 | Completed | All 5 database models implemented. 5 Alembic migration versions created and tested.
T-014 | Implement Pydantic schemas for request/response validation: ScanCreateRequest ScanResponse ScanListResponse ScanResultsResponse. | Zero-Day Scanner for Agriculture Web Portals-Tejas Raksha | Giridhar Pai | 25252 | BCA in Cyber Security, Ethical Hacking & Digital Forensics with IBM | 6th Semester | Week 3 - Backend Development | 2026-04-07 | 2026-04-07 | Completed | All Pydantic schemas implemented with proper validation rules and type hints.
T-015 | Implement API key authentication middleware and CORS configuration. Add rate limiting (60 requests/minute per client). | Zero-Day Scanner for Agriculture Web Portals-Tejas Raksha | Giridhar Pai | 25252 | BCA in Cyber Security, Ethical Hacking & Digital Forensics with IBM | 6th Semester | Week 3 - Backend Development | 2026-04-08 | 2026-04-08 | Completed | Authentication and CORS working. Rate limiting tested and verified.
T-016 | Implement scan management API endpoints: POST /api/v1/scans GET /api/v1/scans GET /api/v1/scans/{id} DELETE /api/v1/scans/{id}. | Zero-Day Scanner for Agriculture Web Portals-Tejas Raksha | Giridhar Pai | 25252 | BCA in Cyber Security, Ethical Hacking & Digital Forensics with IBM | 6th Semester | Week 3 - Backend Development | 2026-04-08 | 2026-04-08 | Completed | All CRUD endpoints for scans implemented and tested with Postman.
T-017 | Implement scan results endpoint GET /api/v1/scans/{id}/results with JSON report parsing and fallback to result_summary. | Zero-Day Scanner for Agriculture Web Portals-Tejas Raksha | Giridhar Pai | 25252 | BCA in Cyber Security, Ethical Hacking & Digital Forensics with IBM | 6th Semester | Week 3 - Backend Development | 2026-04-09 | 2026-04-09 | Completed | Results endpoint working. Fallback logic for historical scans without JSON reports implemented.
T-018 | Implement WebSocket connection manager with Redis pub/sub for real-time scan progress updates. Test sub-second latency. | Zero-Day Scanner for Agriculture Web Portals-Tejas Raksha | Giridhar Pai | 25252 | BCA in Cyber Security, Ethical Hacking & Digital Forensics with IBM | 6th Semester | Week 3 - Backend Development | 2026-04-09 | 2026-04-09 | Completed | WebSocket real-time updates working. Redis pub/sub latency < 100ms confirmed.
T-019 | Implement Celery application configuration with Redis broker. Create run_scan task with 30-minute timeout and progress reporting. | Zero-Day Scanner for Agriculture Web Portals-Tejas Raksha | Giridhar Pai | 25252 | BCA in Cyber Security, Ethical Hacking & Digital Forensics with IBM | 6th Semester | Week 3 - Backend Development | 2026-04-10 | 2026-04-10 | Completed | Celery worker running with concurrency=4. Task state machine implemented correctly.
T-020 | Implement async web crawler: CrawlerController Fetcher Parser Frontier. Configure rate limiting robots.txt respect and depth limits. | Zero-Day Scanner for Agriculture Web Portals-Tejas Raksha | Giridhar Pai | 25252 | BCA in Cyber Security, Ethical Hacking & Digital Forensics with IBM | 6th Semester | Week 3 - Backend Development | 2026-04-10 | 2026-04-10 | Completed | Crawler successfully discovers pages. Tested on testfire.net - 116 pages crawled.
T-021 | Implement BaseCheck abstract class and CheckRegistry pattern. Create CheckContext with URL list and HTTP fetcher. | Zero-Day Scanner for Agriculture Web Portals-Tejas Raksha | Giridhar Pai | 25252 | BCA in Cyber Security, Ethical Hacking & Digital Forensics with IBM | 6th Semester | Week 4 - Security Checks Implementation | 2026-04-11 | 2026-04-11 | Completed | Check registry pattern implemented. New checks can be added without modifying core scanner.
T-022 | Implement XSS detection check with 7 payloads: script tag img onerror svg onload iframe javascript body onload. Test reflected and stored XSS. | Zero-Day Scanner for Agriculture Web Portals-Tejas Raksha | Giridhar Pai | 25252 | BCA in Cyber Security, Ethical Hacking & Digital Forensics with IBM | 6th Semester | Week 4 - Security Checks Implementation | 2026-04-11 | 2026-04-11 | Completed | XSS check detects 482 findings on testfire.net. Accuracy validated against known vulnerabilities.
T-023 | Implement SQL Injection detection: error-based time-based blind boolean-based blind and union-based techniques for MySQL PostgreSQL SQL Server Oracle. | Zero-Day Scanner for Agriculture Web Portals-Tejas Raksha | Giridhar Pai | 25252 | BCA in Cyber Security, Ethical Hacking & Digital Forensics with IBM | 6th Semester | Week 4 - Security Checks Implementation | 2026-04-12 | 2026-04-12 | Completed | SQL injection detected on testphp.vulnweb.com. All 4 techniques working correctly.
T-024 | Implement Security Headers check for CSP X-Frame-Options X-Content-Type-Options HSTS Referrer-Policy Permissions-Policy. | Zero-Day Scanner for Agriculture Web Portals-Tejas Raksha | Giridhar Pai | 25252 | BCA in Cyber Security, Ethical Hacking & Digital Forensics with IBM | 6th Semester | Week 4 - Security Checks Implementation | 2026-04-12 | 2026-04-12 | Completed | Security headers check working. Missing headers correctly identified and reported.
T-025 | Implement Sensitive File Exposure check with 50+ file paths: .env .git/config backup.sql wp-config.php id_rsa Dockerfile. | Zero-Day Scanner for Agriculture Web Portals-Tejas Raksha | Giridhar Pai | 25252 | BCA in Cyber Security, Ethical Hacking & Digital Forensics with IBM | 6th Semester | Week 4 - Security Checks Implementation | 2026-04-13 | 2026-04-13 | Completed | 15 sensitive files detected on pentest-ground.com:5013. All file paths tested correctly.
T-026 | Implement Command Injection check with shell metacharacter payloads. Implement CSRF detection via form token analysis. | Zero-Day Scanner for Agriculture Web Portals-Tejas Raksha | Giridhar Pai | 25252 | BCA in Cyber Security, Ethical Hacking & Digital Forensics with IBM | 6th Semester | Week 4 - Security Checks Implementation | 2026-04-13 | 2026-04-13 | Completed | Command injection and CSRF checks implemented. Tested on DVWA application.
T-027 | Implement XXE Injection SSRF Authentication Bypass Insecure Deserialization and Directory Listing security checks. | Zero-Day Scanner for Agriculture Web Portals-Tejas Raksha | Giridhar Pai | 25252 | BCA in Cyber Security, Ethical Hacking & Digital Forensics with IBM | 6th Semester | Week 4 - Security Checks Implementation | 2026-04-14 | 2026-04-14 | Completed | All 12 security check types implemented. Total check coverage matches OWASP Top 10.
T-028 | Implement Server Version Disclosure check. Implement Finding model with severity title URL description remediation and metadata fields. | Zero-Day Scanner for Agriculture Web Portals-Tejas Raksha | Giridhar Pai | 25252 | BCA in Cyber Security, Ethical Hacking & Digital Forensics with IBM | 6th Semester | Week 4 - Security Checks Implementation | 2026-04-14 | 2026-04-14 | Completed | Server version disclosure detected on testfire.net (Apache-Coyote/1.1). Finding model complete.
T-029 | Implement PDF report generator using ReportLab. Add Tejas Raksha logo severity breakdown table detailed findings and official security stamp. | Zero-Day Scanner for Agriculture Web Portals-Tejas Raksha | Giridhar Pai | 25252 | BCA in Cyber Security, Ethical Hacking & Digital Forensics with IBM | 6th Semester | Week 4 - Security Checks Implementation | 2026-04-15 | 2026-04-15 | Completed | PDF reports generated successfully. Professional branding with logo and stamp verified.
T-030 | Initialize React 18 frontend with Vite 5 and Tailwind CSS 3.3. Configure dark/light theme system with localStorage persistence. | Zero-Day Scanner for Agriculture Web Portals-Tejas Raksha | Giridhar Pai | 25252 | BCA in Cyber Security, Ethical Hacking & Digital Forensics with IBM | 6th Semester | Week 5 - Frontend Development | 2026-04-16 | 2026-04-16 | Completed | React app initialized. Dark theme default working. Theme toggle persists across sessions.
T-031 | Implement Landing Page with animated gradient background scan form advanced options panel and security checks grid. | Zero-Day Scanner for Agriculture Web Portals-Tejas Raksha | Giridhar Pai | 25252 | BCA in Cyber Security, Ethical Hacking & Digital Forensics with IBM | 6th Semester | Week 5 - Frontend Development | 2026-04-16 | 2026-04-16 | Completed | Landing page complete with neural network background animation using Framer Motion.
T-032 | Implement Scan Progress Page with CircularHUD component real-time WebSocket updates live statistics panel and phase timeline. | Zero-Day Scanner for Agriculture Web Portals-Tejas Raksha | Giridhar Pai | 25252 | BCA in Cyber Security, Ethical Hacking & Digital Forensics with IBM | 6th Semester | Week 5 - Frontend Development | 2026-04-17 | 2026-04-17 | Completed | Real-time progress page working. WebSocket updates received and displayed correctly.
T-033 | Implement Results Page with severity summary dashboard findings filter bar paginated findings list and FindingCard component. | Zero-Day Scanner for Agriculture Web Portals-Tejas Raksha | Giridhar Pai | 25252 | BCA in Cyber Security, Ethical Hacking & Digital Forensics with IBM | 6th Semester | Week 5 - Frontend Development | 2026-04-17 | 2026-04-17 | Completed | Results page displays all 484 findings for testfire.net scan. PDF download working.
T-034 | Implement History Page with scan history table platform milestones section and scan comparison selection. | Zero-Day Scanner for Agriculture Web Portals-Tejas Raksha | Giridhar Pai | 25252 | BCA in Cyber Security, Ethical Hacking & Digital Forensics with IBM | 6th Semester | Week 5 - Frontend Development | 2026-04-18 | 2026-04-18 | Completed | History page shows 9 completed scans. Milestones section displays project achievements.
T-035 | Implement Schedules Page with schedule creation form active schedules list enable/disable toggle and next run time display. | Zero-Day Scanner for Agriculture Web Portals-Tejas Raksha | Giridhar Pai | 25252 | BCA in Cyber Security, Ethical Hacking & Digital Forensics with IBM | 6th Semester | Week 5 - Frontend Development | 2026-04-18 | 2026-04-18 | Completed | Schedules page functional. Hourly daily weekly monthly recurrence options working.
T-036 | Implement False Positives Page Integrations Page (Jira Slack Email) and Trends Page with recharts visualizations. | Zero-Day Scanner for Agriculture Web Portals-Tejas Raksha | Giridhar Pai | 25252 | BCA in Cyber Security, Ethical Hacking & Digital Forensics with IBM | 6th Semester | Week 5 - Frontend Development | 2026-04-19 | 2026-04-19 | Completed | All remaining pages implemented. Recharts line bar and pie charts rendering correctly.
T-037 | Implement API service layer (api.js) with axios interceptors. Configure Zustand state management store for global state. | Zero-Day Scanner for Agriculture Web Portals-Tejas Raksha | Giridhar Pai | 25252 | BCA in Cyber Security, Ethical Hacking & Digital Forensics with IBM | 6th Semester | Week 5 - Frontend Development | 2026-04-19 | 2026-04-19 | Completed | API service layer complete with 20+ methods. Zustand store managing theme scan state and errors.
T-038 | Implement false positive management API endpoints. Implement scan comparison endpoint with new/fixed/unchanged finding classification. | Zero-Day Scanner for Agriculture Web Portals-Tejas Raksha | Giridhar Pai | 25252 | BCA in Cyber Security, Ethical Hacking & Digital Forensics with IBM | 6th Semester | Week 6 - Advanced Features | 2026-04-20 | 2026-04-20 | Completed | False positive marking and comparison endpoints working. Comparison correctly identifies delta findings.
T-039 | Implement scheduled scan management API with Celery Beat integration. Support hourly daily weekly monthly recurrence with email notifications. | Zero-Day Scanner for Agriculture Web Portals-Tejas Raksha | Giridhar Pai | 25252 | BCA in Cyber Security, Ethical Hacking & Digital Forensics with IBM | 6th Semester | Week 6 - Advanced Features | 2026-04-20 | 2026-04-20 | Completed | Scheduled scans executing automatically via Celery Beat. Email notifications sent on completion.
T-040 | Implement CVE enrichment service with NVD API integration. Map vulnerability categories to CWE identifiers and fetch relevant CVEs. | Zero-Day Scanner for Agriculture Web Portals-Tejas Raksha | Giridhar Pai | 25252 | BCA in Cyber Security, Ethical Hacking & Digital Forensics with IBM | 6th Semester | Week 6 - Advanced Features | 2026-04-21 | 2026-04-21 | Completed | CVE enrichment working. Findings enriched with relevant CVE IDs and NVD links.
T-041 | Implement Jira integration for automatic issue creation. Implement Slack webhook notifications. Implement SMTP email service. | Zero-Day Scanner for Agriculture Web Portals-Tejas Raksha | Giridhar Pai | 25252 | BCA in Cyber Security, Ethical Hacking & Digital Forensics with IBM | 6th Semester | Week 6 - Advanced Features | 2026-04-21 | 2026-04-21 | Completed | All 3 integrations working. Jira issues created for high-severity findings automatically.
T-042 | Implement SAST integration with Bandit (Python) and Semgrep (multi-language). Add finding lifecycle tracking models. | Zero-Day Scanner for Agriculture Web Portals-Tejas Raksha | Giridhar Pai | 25252 | BCA in Cyber Security, Ethical Hacking & Digital Forensics with IBM | 6th Semester | Week 6 - Advanced Features | 2026-04-22 | 2026-04-22 | Completed | SAST integration complete. Bandit and Semgrep scans producing findings correctly.
T-043 | Fix worker/init.py missing file. Create worker/adaptive_tasks.py placeholder. Fix celery_app.py include list for lifecycle_tasks. | Zero-Day Scanner for Agriculture Web Portals-Tejas Raksha | Giridhar Pai | 25252 | BCA in Cyber Security, Ethical Hacking & Digital Forensics with IBM | 6th Semester | Week 6 - Advanced Features | 2026-04-22 | 2026-04-22 | Completed | Critical bug fixed. Worker and Beat containers now start successfully. All 6 containers healthy.
T-044 | Fix findings.py route: convert from synchronous Session to async AsyncSession. Fix all 8 endpoints to use await db.execute(select(...)). | Zero-Day Scanner for Agriculture Web Portals-Tejas Raksha | Giridhar Pai | 25252 | BCA in Cyber Security, Ethical Hacking & Digital Forensics with IBM | 6th Semester | Week 6 - Advanced Features | 2026-04-23 | 2026-04-23 | Completed | API no longer crashes on startup. All findings endpoints working with async database access.
T-045 | Fix schedules.py UUID bug (str(UUID) to str(uuid.uuid4())). Fix models/init.py to export all 13 models. Fix docker-compose DATABASE_URL_SYNC. | Zero-Day Scanner for Agriculture Web Portals-Tejas Raksha | Giridhar Pai | 25252 | BCA in Cyber Security, Ethical Hacking & Digital Forensics with IBM | 6th Semester | Week 6 - Advanced Features | 2026-04-23 | 2026-04-23 | Completed | All runtime bugs fixed. Schedule creation working. Worker database connections using correct sync URL.
T-046 | Conduct live scan on http://testfire.net. Monitor real-time progress via WebSocket. Verify 484 findings detected in 308.5 seconds. | Zero-Day Scanner for Agriculture Web Portals-Tejas Raksha | Giridhar Pai | 25252 | BCA in Cyber Security, Ethical Hacking & Digital Forensics with IBM | 6th Semester | Week 7 - Testing & Validation | 2026-04-24 | 2026-04-24 | Completed | Live scan completed successfully. 484 findings (482 High 2 Low) across 108 pages. JSON and HTML reports generated.
T-047 | Conduct live scan on http://testphp.vulnweb.com. Verify SQL injection and XSS detection. Validate 292 findings including MySQL error-based SQLi. | Zero-Day Scanner for Agriculture Web Portals-Tejas Raksha | Giridhar Pai | 25252 | BCA in Cyber Security, Ethical Hacking & Digital Forensics with IBM | 6th Semester | Week 7 - Testing & Validation | 2026-04-24 | 2026-04-24 | Completed | 292 findings detected. SQL injection confirmed with MySQL error messages. XSS in multiple parameters.
T-048 | Conduct scans on pentest-ground.com targets: DVWA (port 4280) DVGA (port 5013) RestFlaw (port 9000) ShadowLogic (port 7001) GuardianLeaks (port 81). | Zero-Day Scanner for Agriculture Web Portals-Tejas Raksha | Giridhar Pai | 25252 | BCA in Cyber Security, Ethical Hacking & Digital Forensics with IBM | 6th Semester | Week 7 - Testing & Validation | 2026-04-25 | 2026-04-25 | Completed | 5 scans completed. 18 sensitive file exposures on port 5013. 3 findings on port 81. Results stored in history.
T-049 | Run integration test suite: TestHealthCheck TestScanWorkflow TestAuthentication TestValidation TestDatabase TestPerformance. | Zero-Day Scanner for Agriculture Web Portals-Tejas Raksha | Giridhar Pai | 25252 | BCA in Cyber Security, Ethical Hacking & Digital Forensics with IBM | 6th Semester | Week 7 - Testing & Validation | 2026-04-25 | 2026-04-25 | Completed | All 6 test classes passed. API response time < 100ms. 95%+ code coverage achieved.
T-050 | Run end-to-end tests with Playwright: complete scan workflow dark mode toggle responsive design form validation navigation. | Zero-Day Scanner for Agriculture Web Portals-Tejas Raksha | Giridhar Pai | 25252 | BCA in Cyber Security, Ethical Hacking & Digital Forensics with IBM | 6th Semester | Week 7 - Testing & Validation | 2026-04-26 | 2026-04-26 | Completed | All E2E tests passed. Frontend tested at Desktop Tablet and Mobile viewports.
T-051 | Insert real scan data from PDF reports into database. Create JSON report files for all 8 historical scans. Verify findings count matches. | Zero-Day Scanner for Agriculture Web Portals-Tejas Raksha | Giridhar Pai | 25252 | BCA in Cyber Security, Ethical Hacking & Digital Forensics with IBM | 6th Semester | Week 7 - Testing & Validation | 2026-04-26 | 2026-04-26 | Completed | All 8 historical scans have complete findings. API returns correct counts: 484 75 93 18 165 292 1 1.
T-052 | Performance testing: measure scan throughput API response times concurrent request handling and PDF generation speed. | Zero-Day Scanner for Agriculture Web Portals-Tejas Raksha | Giridhar Pai | 25252 | BCA in Cyber Security, Ethical Hacking & Digital Forensics with IBM | 6th Semester | Week 7 - Testing & Validation | 2026-04-27 | 2026-04-27 | Completed | Scanner: 22.5 pages/min. API health: <10ms. PDF generation: 2-5 seconds. 10 concurrent requests handled.
T-053 | Write comprehensive API reference documentation (25+ endpoints). Write User Manual (50+ pages). Write Developer Guide and Operations Runbook. | Zero-Day Scanner for Agriculture Web Portals-Tejas Raksha | Giridhar Pai | 25252 | BCA in Cyber Security, Ethical Hacking & Digital Forensics with IBM | 6th Semester | Week 7 - Testing & Validation | 2026-04-27 | 2026-04-27 | Completed | All documentation completed. Postman collection with all endpoints created and exported.
T-054 | Create TEJAS_RAKSHA_START.bat one-click startup script with Docker health checks service verification and browser auto-open. | Zero-Day Scanner for Agriculture Web Portals-Tejas Raksha | Giridhar Pai | 25252 | BCA in Cyber Security, Ethical Hacking & Digital Forensics with IBM | 6th Semester | Week 7 - Testing & Validation | 2026-04-28 | 2026-04-28 | Completed | One-click startup script working. All 6 containers start reliably. Browser opens automatically.
T-055 | Write Final Project Report (55+ pages): Background System Requirements Design Implementation Testing GUI Snapshots Conclusions References Appendix. | Zero-Day Scanner for Agriculture Web Portals-Tejas Raksha | Giridhar Pai | 25252 | BCA in Cyber Security, Ethical Hacking & Digital Forensics with IBM | 6th Semester | Week 7 - Testing & Validation | 2026-04-28 | 2026-04-28 | Completed | Final report completed: 27500+ words 4617 lines 23 appendices. All sections thoroughly documented.
T-056 | Final project review with mentor. Demonstrate live scan on testfire.net. Present PDF report. Review all features and deliverables. | Zero-Day Scanner for Agriculture Web Portals-Tejas Raksha | Giridhar Pai | 25252 | BCA in Cyber Security, Ethical Hacking & Digital Forensics with IBM | 6th Semester | Week 7 - Testing & Validation | 2026-04-29 | 2026-04-29 | Completed | Final review passed. Mentor approved all deliverables. Project declared complete and production-ready.
T-057 | Project handover: submit source code documentation test results scan reports and final report. Complete internship evaluation form. | Zero-Day Scanner for Agriculture Web Portals-Tejas Raksha | Giridhar Pai | 25252 | BCA in Cyber Security, Ethical Hacking & Digital Forensics with IBM | 6th Semester | Week 7 - Completion | 2026-04-30 | 2026-04-30 | Completed | All deliverables submitted. Internship successfully completed. Platform deployed and operational.